## void mainMenu()
Test Suite 1 - Main menu testing (Start-up page)
Test case 1 | Test Details
| ID | 1 | Created by | Kristian Lalev
| Function | void mainMenu() | Created on | 2021-02-22
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-25
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To be sent to void loginMenu() | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (9) | 9 | The program is terminated | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 1.1 | Created by | Kristian Lalev
| Function | void mainMenu() | Created on | 2021-02-23
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To be sent to void loginMenu() | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (9) | 9 | The program is terminated | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 1.2 | Created by | Kristian Lalev
| Function | void mainMenu() | Created on | 2021-02-23
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To be sent to void loginMenu() | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (9) | 9 | The program is terminated | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 1.3 | Created by | Kristian Lalev
| Function | void mainMenu() | Created on | 2021-02-24
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To be sent to void loginMenu() | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (2) | 2 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (9) | 9 | The program is terminated | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void loginMenu()
Test Suite 2 - Login menu testing (to log in the system if you have already an account)
Test case 1 | Test Details
| ID | 2 | Created by | Kristian Lalev
| Function | void loginMenu() | Created on | 2021-02-23
| Description | The login function is logging the people in the system if they have already an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Type your e-mail | neshtosi@codingburgas.bg | To accept the e-mail if it is correct | As expected | PASSED | The function is working properly
| 1.2 | Type your password | Neshtosi12 | To accept the password if it is correct | As expected | PASSED | The function is working properly
| 1.3 | If you don’t have an account, type 1 to register | 1 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (unvalid numeric) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 2.1 | Created by | Kristian Lalev
| Function | void loginMenu() | Created on | 2021-02-23
| Description | The login function is logging the people in the system if they have already an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Type your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 2.2 | Type your password | Neshtosi12 | To accept the password if it is correct | As expected | PASSED | The function is working properly
| 2.3 | If you don’t have an account, type 1 to register | 1 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (unvalid numeric) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 2.2 | Created by | Kristian Lalev
| Function | void loginMenu() | Created on | 2021-02-24
| Description | The login function is logging the people in the system if they have already an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Type your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 3.2 | Type your password | Neshtosi12 | To accept the password if it is correct | As expected | PASSED | The function is working properly
| 3.3 | If you don’t have an account, type 1 to register | 1 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (unvalid numeric) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 2.3 | Created by | Kristian Lalev
| Function | void loginMenu() | Created on | 2021-02-24
| Description | The login function is logging the people in the system if they have already an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Type your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 4.2 | Type your password | Neshtosi12 | To accept the password if it is correct | As expected | PASSED | The function is working properly
| 4.3 | If you don’t have an account, type 1 to register | 1 | To be sent to void registerMenu() | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (unvalid numeric) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void registerMenu()
Test Suite 3 - Register menu testing (register in the system)
Test case 1 | Test Details
| ID | 3 | Created by | Kristian Lalev
| Function | void RegisterMenu() | Created on | 2021-02-22
| Description | The register function is registering the people in the system if they have not an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Enter your name | Goshko | To accept the name | As expected | PASSED | The function is working properly
| 1.2 | Enter your surname | Peshkov | To accept the surname | As expected | PASSED | The function is working properly
| 1.3 | Enter your password (between 5 and 10 symbols) | Neshtosi12 | To accept the password | As expected | PASSED | The function is working properly
| 1.4 | Enter your class | 10A | To accept the class | As expected | PASSED | The function is working properly
| 1.5 | Enter your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 1.6 | Enter your role | QA engineer | To accept the role and be distributed in the QAs list | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 3.1 | Created by | Kristian Lalev
| Function | void RegisterMenu() | Created on | 2021-02-23
| Description | The register function is registering the people in the system if they have not an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Enter your name | Goshko | To accept the name | As expected | PASSED | The function is working properly
| 2.2 | Enter your surname | Peshkov | To accept the surname | As expected | PASSED | The function is working properly
| 2.3 | Enter your password (between 5 and 10 symbols) | Neshtosi12 | To accept the password | As expected | PASSED | The function is working properly
| 2.4 | Enter your class | 10A | To accept the class | As expected | PASSED | The function is working properly
| 2.5 | Enter your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 2.6 | Enter your role | QA engineer | To accept the role and be distributed in the QAs list | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 3.2 | Created by | Kristian Lalev
| Function | void RegisterMenu() | Created on | 2021-02-23
| Description | The register function is registering the people in the system if they have not an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Enter your name | Goshko | To accept the name | As expected | PASSED | The function is working properly
| 3.2 | Enter your surname | Peshkov | To accept the surname | As expected | PASSED | The function is working properly
| 3.3 | Enter your password (between 5 and 10 symbols) | Neshtosi12 | To accept the password | As expected | PASSED | The function is working properly
| 3.4 | Enter your class | 10A | To accept the class | As expected | PASSED | The function is working properly
| 3.5 | Enter your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 3.6 | Enter your role | QA engineer | To accept the role and be distributed in the QAs list | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 3.3 | Created by | Kristian Lalev
| Function | void RegisterMenu() | Created on | 2021-02-24
| Description | The register function is registering the people in the system if they have not an account. | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Enter your name | Goshko | To accept the name | As expected | PASSED | The function is working properly
| 4.2 | Enter your surname | Peshkov | To accept the surname | As expected | PASSED | The function is working properly
| 4.3 | Enter your password (between 5 and 10 symbols) | Neshtosi12 | To accept the password | As expected | PASSED | The function is working properly
| 4.4 | Enter your class | 10A | To accept the class | As expected | PASSED | The function is working properly
| 4.5 | Enter your e-mail | neshtosi@codingburgas.bg | To accept the e-mail | As expected | PASSED | The function is working properly
| 4.6 | Enter your role | QA engineer | To accept the role and be distributed in the QAs list | As expected | PASSED | The function is working properly

## void scrumMasterMenu()
Test Suite 4 - Scrum Mater menu testing (the people, logged as Scrum Masters are there)
Test case 1 | Test Details
| ID | 4 | Created by | Kristian Lalev
| Function | void scrumMasterMenu() | Created on | 2021-02-20
| Description | This Scrum Master function is showed if you are student and you are regustered as Scrum Master role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-24
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To crreate your team | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | void teamMenu() | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (3) | 3 | To email the admin for something | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 1.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 4.1 | Created by | Kristian Lalev
| Function | void scrumMasterMenu() | Created on | 2021-02-21
| Description | This Scrum Master function is showed if you are student and you are regustered as Scrum Master role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-24
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To crreate your team | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To check about your team | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (3) | 3 | To email the admin for something | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 2.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 4.2 | Created by | Kristian Lalev
| Function | void scrumMasterMenu() | Created on | 2021-02-22
| Description | This Scrum Master function is showed if you are student and you are regustered as Scrum Master role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-24
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To crreate your team | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To check about your team | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (3) | 3 | To email the admin for something | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 3.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 4.3 | Created by | Kristian Lalev
| Function | void scrumMasterMenu() | Created on | 2021-02-22
| Description | This Scrum Master function is showed if you are student and you are regustered as Scrum Master role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-24
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To crreate your team | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (2) | 2 | To check about your team | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (3) | 3 | To email the admin for something | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 4.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void frontEndMenu()
Test Suite 5 - Front-End menu testing (the people, logged as Front-end are there)
Test case 1 | Test Details
| ID | 5 | Created by | Kristian Lalev
| Function | void frontEndMenu() | Created on | 2021-02-20
| Description | This Front-End function is showed if you are student and you are regustered as Front-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 5.1 | Created by | Kristian Lalev
| Function | void frontEndMenu() | Created on | 2021-02-21
| Description | This Front-End function is showed if you are student and you are regustered as Front-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 5.2 | Created by | Kristian Lalev
| Function | void frontEndMenu() | Created on | 2021-02-21
| Description | This Front-End function is showed if you are student and you are regustered as Front-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 5.3 | Created by | Kristian Lalev
| Function | void frontEndMenu() | Created on | 2021-02-22
| Description | This Front-End function is showed if you are student and you are regustered as Front-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void backEndMenu()
Test Suite 6 - Back-End menu testing (the people, logged as Back-end are there)
Test case 1 | Test Details
| ID | 6 | Created by | Kristian Lalev
| Function | void backEndMenu() | Created on | 2021-02-19
| Description | This Front-End function is showed if you are student and you are regustered as Front-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 6.1 | Created by | Kristian Lalev
| Function | void backEndMenu() | Created on | 2021-02-20
| Description | This Back-End function is showed if you are student and you are regustered as Back-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 6.2 | Created by | Kristian Lalev
| Function | void backEndMenu() | Created on | 2021-02-21
| Description | This Back-End function is showed if you are student and you are regustered as Back-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 6.3 | Created by | Kristian Lalev
| Function | void backEndMenu() | Created on | 2021-02-22
| Description | This Back-End function is showed if you are student and you are regustered as Back-end role | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (9) | 2 | To log out of the system | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void QAEngineerMenu()
Test Suite 7 - QAEngineer menu testing (the people, logged as QAEngineer are there)
Test case 1 | Test Details
| ID | 7 | Created by | Kristian Lalev
| Function | void QAEngineerMenu() | Created on | 2021-02-19
| Description | This QAEngineer function is showed if you are student and you are regustered as QAEngineer | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | void teamMenu() | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | To report bugs if you have. | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 7.1 | Created by | Kristian Lalev
| Function | void QAEngineerMenu() | Created on | 2021-02-20
| Description | This QAEngineer function is showed if you are student and you are regustered as QAEngineer | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To check your team | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To report bugs if you have. | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (9) | 9 | To logout of the system | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 7.2 | Created by | Kristian Lalev
| Function | void QAEngineerMenu() | Created on | 2021-02-20
| Description | This QAEngineer function is showed if you are student and you are regustered as QAEngineer | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To check your team | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To report bugs if you have. | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (9) | 9 | To logout of the system | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 7.3 | Created by | Kristian Lalev
| Function | void QAEngineerMenu() | Created on | 2021-02-21
| Description | This QAEngineer function is showed if you are student and you are regustered as QAEngineer | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To check your team | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (2) | 2 | To report bugs if you have. | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (9) | 9 | To logout of the system | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void teacherMenu()
Test Suite 8 - Main menu testing (Start-up page for login/register)
Test case 1 | Test Details
| ID | 8 | Created by | Kristian Lalev
| Function | void teachersMenu() | Created on | 2021-02-23
| Description | This functions shows if you are registered as teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 8.1 | Created by | Kristian Lalev
| Function | void teachersMenu() | Created on | 2021-02-24
| Description | This functions shows if you are registered as teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 8.2 | Created by | Kristian Lalev
| Function | void teachersMenu() | Created on | 2021-02-24
| Description | This functions shows if you are registered as teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 8.3 | Created by | Kristian Lalev
| Function | void teachersMenu() | Created on | 2021-02-25
| Description | This functions shows if you are registered as teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To be sent to void teamMenu() | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (everything except 1 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void adminMenu()
Test Suite 9 - Admin menu testing (Start-up page for login/register)
Test case 1 | Test Details
| ID | 9 | Created by | Kristian Lalev
| Function | void adminMenu() | Created on | 2021-02-22
| Description | This functions only shows if you are an admin and you can control the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To manage some account in the system | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | To manage the school | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (3) | 3 | To check your mailbox | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (4) | 4 | To add teachers in the system | As expected | PASSED | The function is working properly
| 1.5 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 1.6 | Entering option choice (everything except 1,2,3,4 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 9.1 | Created by | Kristian Lalev
| Function | void adminMenu() | Created on | 2021-02-23
| Description | This functions only shows if you are an admin and you can control the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To manage some account in the system | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To manage the school | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (3) | 3 | To check your mailbox | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (4) | 4 | To add teachers in the system | As expected | PASSED | The function is working properly
| 2.5 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 2.6 | Entering option choice (everything except 1,2,3,4 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 9.2 | Created by | Kristian Lalev
| Function | void adminMenu() | Created on | 2021-02-24
| Description | This functions only shows if you are an admin and you can control the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To manage some account in the system | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To manage the school | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (3) | 3 | To check your mailbox | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (4) | 4 | To add teachers in the system | As expected | PASSED | The function is working properly
| 3.5 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 3.6 | Entering option choice (everything except 1,2,3,4 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 9.3 | Created by | Kristian Lalev
| Function | void adminMenu() | Created on | 2021-02-25
| Description | This functions only shows if you are an admin and you can control the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To manage some account in the system | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (2) | 2 | To manage the school | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (3) | 3 | To check your mailbox | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (4) | 4 | To add teachers in the system | As expected | PASSED | The function is working properly
| 4.5 | Entering option choice (9) | 9 | To log out of the system | As expected | PASSED | The function is working properly
| 4.6 | Entering option choice (everything except 1,2,3,4 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void viewMenu()
Test Suite 10 - View Menu testing (The list with all of students, teachers, teams and to search by criteria)
Test case 1 | Test Details
| ID | 10 | Created by | Kristian Lalev
| Function | void viewMenu() | Created on | 2021-02-22
| Description | This functions shows the list with all of the participants in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To see the list with all students | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | To see the list with all teachers | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (3) | 3 | The program is teams | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (4) | 4 | To see the lists with some specific criteria | As expected | PASSED | The function is working properly
| 1.5 | Entering option choice (9) | 9 | The program sends you back | As expected | PASSED | The function is working properly
| 1.6 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 10.1 | Created by | Kristian Lalev
| Function | void viewMenu() | Created on | 2021-02-23
| Description | This functions shows the list with all of the participants in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To see the list with all students | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To see the list with all teachers | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (3) | 3 | The program is teams | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (4) | 4 | To see the lists with some specific criteria | As expected | PASSED | The function is working properly
| 2.5 | Entering option choice (9) | 9 | The program sends you back | As expected | PASSED | The function is working properly
| 2.6 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 10.2 | Created by | Kristian Lalev
| Function | void viewMenu() | Created on | 2021-02-23
| Description | This functions shows the list with all of the participants in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To see the list with all students | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To see the list with all teachers | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (3) | 3 | The program is teams | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (4) | 4 | To see the lists with some specific criteria | As expected | PASSED | The function is working properly
| 3.5 | Entering option choice (9) | 9 | The program sends you back | As expected | PASSED | The function is working properly
| 3.6 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 10.3 | Created by | Kristian Lalev
| Function | void viewMenu() | Created on | 2021-02-24
| Description | This functions shows the list with all of the participants in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Entering option choice (1) | 1 | To see the list with all students | As expected | PASSED | The function is working properly
| 4.2 | Entering option choice (2) | 2 | To see the list with all teachers | As expected | PASSED | The function is working properly
| 4.3 | Entering option choice (3) | 3 | The program is teams | As expected | PASSED | The function is working properly
| 4.4 | Entering option choice (4) | 4 | To see the lists with some specific criteria | As expected | PASSED | The function is working properly
| 4.5 | Entering option choice (9) | 9 | The program sends you back | As expected | PASSED | The function is working properly
| 4.6 | Entering option choice (everything except 1,2 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void teamMenu()
Test Suite 11 - Team Menu testing (creating a team)
Test case 1 | Test Details
| ID | 11 | Created by | Kristian Lalev
| Function | void teamMenu() | Created on | 2021-02-21
| Description | This functions creats a team for you (works only for the Scrum Masters) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Your team name | ZaFe |  | As expected | PASSED | The function is working properly
| 1.1 | Description of the team | We are amazing | To write something distinctive for your team | As expected | PASSED | The function is working properly
| 1.2 | Set up date | 2021-03-05 | The date for presenting your project | As expected | PASSED | The function is working properly
| 1.3 | Check who is free for your team (Back-end, Front-end, QAEngineer) | Gosho, Pesho, Qnko | To register Gosho, Pesho and Qnko when you agreed with each other | As expected | PASSED | The function is working properly
| 1.4 | Add a teacher to your team | Danaila Stamatova | To add Danaila Stamatova to yur team | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 11.1 | Created by | Kristian Lalev
| Function | void teamMenu() | Created on | 2021-02-22
| Description | This functions creats a team for you (works only for the Scrum Masters) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Your team name | ZaFe |  | As expected | PASSED | The function is working properly
| 2.1 | Description of the team | We are amazing | To write something distinctive for your team | As expected | PASSED | The function is working properly
| 2.2 | Set up date | 2021-03-05 | The date for presenting your project | As expected | PASSED | The function is working properly
| 2.3 | Check who is free for your team (Back-end, Front-end, QAEngineer) | Gosho, Pesho, Qnko | To register Gosho, Pesho and Qnko when you agreed with each other | As expected | PASSED | The function is working properly
| 2.4 | Add a teacher to your team | Danaila Stamatova | To add Danaila Stamatova to yur team | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 11.2 | Created by | Kristian Lalev
| Function | void teamMenu() | Created on | 2021-02-23
| Description | This functions creats a team for you (works only for the Scrum Masters) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Your team name | ZaFe |  | As expected | PASSED | The function is working properly
| 3.1 | Description of the team | We are amazing | To write something distinctive for your team | As expected | PASSED | The function is working properly
| 3.2 | Set up date | 2021-03-05 | The date for presenting your project | As expected | PASSED | The function is working properly
| 3.3 | Check who is free for your team (Back-end, Front-end, QAEngineer) | Gosho, Pesho, Qnko | To register Gosho, Pesho and Qnko when you agreed with each other | As expected | PASSED | The function is working properly
| 3.4 | Add a teacher to your team | Danaila Stamatova | To add Danaila Stamatova to yur team | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 11.3 | Created by | Kristian Lalev
| Function | void teamMenu() | Created on | 2021-02-24
| Description | This functions creats a team for you (works only for the Scrum Masters) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Your team name | ZaFe |  | As expected | PASSED | The function is working properly
| 4.1 | Description of the team | We are amazing | To write something distinctive for your team | As expected | PASSED | The function is working properly
| 4.2 | Set up date | 2021-03-05 | The date for presenting your project | As expected | PASSED | The function is working properly
| 4.3 | Check who is free for your team (Back-end, Front-end, QAEngineer) | Gosho, Pesho, Qnko | To register Gosho, Pesho and Qnko when you agreed with each other | As expected | PASSED | The function is working properly
| 4.4 | Add a teacher to your team | Danaila Stamatova | To add Danaila Stamatova to yur team | As expected | PASSED | The function is working properly

## void teacherRegisterMenu()
Test Suite 12 - Teacher register menu testing (The function that registers the teachers by the admins)
Test case 1 | Test Details
| ID | 12 | Created by | Kristian Lalev
| Function | void teacherRegisterMenu() | Created on | 2021-02-23
| Description | This function registers the teachers by he admins | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Name | Danaila | To accept the name Danaila | As expected | PASSED | The function is working properly
| 1.2 | Surname | Stamatova | To accept the surname Stamatova | As expected | PASSED | The function is working properly
| 1.3 | Email | dstamatova@codingburgas.bg | To accept the email of the teacher | As expected | PASSED | The function is working properly
| 1.4 | Entering another choice | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 12.1 | Created by | Kristian Lalev
| Function | void teacherRegisterMenu() | Created on | 2021-02-24
| Description | This function registers the teachers by he admins | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Name | Danaila | To accept the name Danaila | As expected | PASSED | The function is working properly
| 2.2 | Surname | Stamatova | To accept the surname Stamatova | As expected | PASSED | The function is working properly
| 2.3 | Email | dstamatova@codingburgas.bg | To accept the email of the teacher | As expected | PASSED | The function is working properly
| 2.4 | Entering another choice | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 12.2 | Created by | Kristian Lalev
| Function | void teacherRegisterMenu() | Created on | 2021-02-24
| Description | This function registers the teachers by he admins | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Name | Danaila | To accept the name Danaila | As expected | PASSED | The function is working properly
| 3.2 | Surname | Stamatova | To accept the surname Stamatova | As expected | PASSED | The function is working properly
| 3.3 | Email | dstamatova@codingburgas.bg | To accept the email of the teacher | As expected | PASSED | The function is working properly
| 3.4 | Entering another choice | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 4 | Test Details
| ID | 12.3 | Created by | Kristian Lalev
| Function | void teacherRegisterMenu() | Created on | 2021-02-25
| Description | This function registers the teachers by he admins | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 4 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 4.1 | Name | Danaila | To accept the name Danaila | As expected | PASSED | The function is working properly
| 4.2 | Surname | Stamatova | To accept the surname Stamatova | As expected | PASSED | The function is working properly
| 4.3 | Email | dstamatova@codingburgas.bg | To accept the email of the teacher | As expected | PASSED | The function is working properly
| 4.4 | Entering another choice | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## struct STUDENT
Test Suite 13 - Student struct testing (the information about the student)
Test case 1 | Test Details
| ID | 13 | Created by | Kristian Lalev
| Function | struct STUDENTS | Created on | 2021-02-18
| Description | This structure shows you the most important infromation about every student in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the structure |  |  | As expected | PASSED | The function is working properly
| 1.1 | The name of the student | Kristian | To show the name in the list | As expected | PASSED | The function is working properly
| 1.2 | The surname of the student | Lalev | To show the surname in the list | As expected | PASSED | The function is working properly
| 1.3 | The password of the student | Neshtosi12 | The password which is hidden | As expected | PASSED | The function is working properly
| 1.4 | The class of the student | 10g | To show the class in the list | As expected | PASSED | The function is working properly
| 1.5 | The role of the student | QAEngineer | To show the role in the list | As expected | PASSED | The function is working properly
| 1.6 | The email of the student | KALalev18@codingburgas.bg | To show the email (for inquires) | As expected | PASSED | The function is working properly
| 1.7 | The id of the student | 1 | The account's id | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 13.1 | Created by | Kristian Lalev
| Function | struct STUDENTS | Created on | 2021-02-19
| Description | This structure shows you the most important infromation about every student in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the structure |  |  | As expected | PASSED | The function is working properly
| 2.1 | The name of the student | Kristian | To show the name in the list | As expected | PASSED | The function is working properly
| 2.2 | The surname of the student | Lalev | To show the surname in the list | As expected | PASSED | The function is working properly
| 2.3 | The password of the student | Neshtosi12 | The password which is hidden | As expected | PASSED | The function is working properly
| 2.4 | The class of the student | 10g | To show the class in the list | As expected | PASSED | The function is working properly
| 2.5 | The role of the student | QAEngineer | To show the role in the list | As expected | PASSED | The function is working properly
| 2.6 | The email of the student | KALalev18@codingburgas.bg | To show the email (for inquires) | As expected | PASSED | The function is working properly
| 2.7 | The id of the student | 1 | The account's id | As expected | PASSED | The function is working properly

## struct TEAM
Test Suite 14 - Struct team testing (The team that you in)
Test case 1 | Test Details
| ID | 14 | Created by | Kristian Lalev
| Function | struct TEAM | Created on | 2021-02-18
| Description | This structure shows you the team that you in with the roles | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the structure |  |  | As expected | PASSED | The function is working properly
| 1.1 | The name of the team | ZaFe | To show the name of the team | As expected | PASSED | The function is working properly
| 1.2 | The description of the team | Qko e da znaesh | To show the surname in the list | As expected | PASSED | The function is working properly
| 1.3 | The data for presenting | 2021-03-05 | To show the data for presenting | As expected | PASSED | The function is working properly
| 1.4 | The teacher in your team | Danaila Stamatova | To show the teacher in your team | As expected | PASSED | The function is working properly
| 1.5 | The Back-end in your team | Plamen Kostov | To show the Back-end name | As expected | PASSED | The function is working properly
| 1.6 | The Front-end in your team | Ilian Yanev | To show the Front-end name | As expected | PASSED | The function is working properly
| 1.7 | The QAEngineer in your team | Kristian Lalev | To show the QAEngineer name | As expected | PASSED | The function is working properly
| 1.8 | The team status | Happy | To show the status of the team | As expected | PASSED | The function is working properly
Test Details
Test case 2 | ID | 14.1 | Created by | Kristian Lalev
| Function | struct TEAM | Created on | 2021-02-19
| Description | This structure shows you the team that you in with the roles | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the structure |  |  | As expected | PASSED | The function is working properly
| 2.1 | The name of the team | ZaFe | To show the name of the team | As expected | PASSED | The function is working properly
| 2.2 | The description of the team | Qko e da znaesh | To show the surname in the list | As expected | PASSED | The function is working properly
| 2.3 | The data for presenting | 2021-03-05 | To show the data for presenting | As expected | PASSED | The function is working properly
| 2.4 | The teacher in your team | Danaila Stamatova | To show the teacher in your team | As expected | PASSED | The function is working properly
| 2.5 | The Back-end in your team | Plamen Kostov | To show the Back-end name | As expected | PASSED | The function is working properly
| 2.6 | The Front-end in your team | Ilian Yanev | To show the Front-end name | As expected | PASSED | The function is working properly
| 2.7 | The QAEngineer in your team | Kristian Lalev | To show the QAEngineer name | As expected | PASSED | The function is working properly
| 2.8 | The team status | Happy | To show the status of the team | As expected | PASSED | The function is working properly

## struct TEACHER
Test Suite 15 - Teacher struct testing (the info about the teacher)
Test case 1 | Test Details
| ID | 15 | Created by | Kristian Lalev
| Function | struct TEACHER | Created on | 2021-02-18
| Description | This structure shows the information about some teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Showing the name of the teacher | Danaila | To show the name of the teacher | As expected | PASSED | The function is working properly
| 1.2 | Showing the surname of the teacher | Stamatova | To show the surname of the teacher | As expected | PASSED | The function is working properly
| 1.3 | Email of the teacher | dstamatova@codingburgas.bg | To show the teacherr's email | As expected | PASSED | The function is working properly
| 1.4 | The ID of the teacher | 5 | Special Id for the teacher | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 15.1 | Created by | Kristian Lalev
| Function | struct TEACHER | Created on | 2021-02-19
| Description | This structure shows the information about some teacher | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Showing the name of the teacher | Danaila | To show the name of the teacher | As expected | PASSED | The function is working properly
| 2.2 | Showing the surname of the teacher | Stamatova | To show the surname of the teacher | As expected | PASSED | The function is working properly
| 2.3 | Email of the teacher | dstamatova@codingburgas.bg | To show the teacherr's email | As expected | PASSED | The function is working properly
| 2.4 | The ID of the teacher | 5 | Special Id for the teacher | As expected | PASSED | The function is working properly

## struct SCHOOL
Test Suite 16 - School struct testing (the info about the school)
Test case 1 | Test Details
| ID | 16 | Created by | Kristian Lalev
| Function | struct TEACHER | Created on | 2021-02-18
| Description | This structure shows the information about your school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Showing the name of the school | PGKPI | To show the name of the school | As expected | PASSED | The function is working properly
| 1.2 | Showing the town of the school | Burgas | To show the town of the school | As expected | PASSED | The function is working properly
| 1.3 | Address of the school | Zahari Stoyanov 8009 | To show the address of the school | As expected | PASSED | The function is working properly
Test Details
Test case 2 | ID | 16.1 | Created by | Kristian Lalev
| Function | struct TEACHER | Created on | 2021-02-19
| Description | This structure shows the information about your school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-02-27
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Showing the name of the school | PGKPI | To show the name of the school | As expected | PASSED | The function is working properly
| 2.2 | Showing the town of the school | Burgas | To show the town of the school | As expected | PASSED | The function is working properly
| 2.3 | Address of the school | Zahari Stoyanov 8009 | To show the address of the school | As expected | PASSED | The function is working properly

## struct EMAIL
Test Suite 17 - Email struct testing (the info about your email)
Test case 1 | Test Details
| ID | 17 | Created by | Kristian Lalev
| Function | struct EMAIL | Created on | 2021-03-05
| Description | This functions is about your email | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Showing the Email | kalalev18@codingburgas.bg | To show the email | As expected | PASSED | The function is working properly
| 1.2 | Showing the dexcription of the email | Burgas | To show the description of the email | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 17.1 | Created by | Kristian Lalev
| Function | struct EMAIL | Created on | 2021-03-06
| Description | This functions is about your email | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Showing the Email | kalalev18@codingburgas.bg | To show the email | As expected | PASSED | The function is working properly
| 2.2 | Showing the dexcription of the email | Burgas | To show the description of the email | As expected | PASSED | The function is working properly

## void emailMenu()
Test Suite 18 - Email Menu testing
Test case 1 | Test Details
| ID | 18 | Created by | Kristian Lalev
| Function | void emailMenu() | Created on | 2021-03-04
| Description | This function checks your name and description | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Enter your name | kristian | Your name to be accepted by the system | As expected | PASSED | The function is working properly
| 1.2 | Enter description of your team | notuse | To accept the description of your team | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 18.1 | Created by | Kristian Lalev
| Function | void emailMenu() | Created on | 2021-03-04
| Description | This function checks your name and description | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Enter your name | kristian | Your name to be accepted by the system | As expected | PASSED | The function is working properly
| 2.2 | Enter description of your team | notuse | To accept the description of your team | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 18.2 | Created by | Kristian Lalev
| Function | void emailMenu() | Created on | 2021-03-05
| Description | This function checks your name and description | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Enter your name | kristian | Your name to be accepted by the system | As expected | PASSED | The function is working properly
| 3.2 | Enter description of your team | notuse | To accept the description of your team | As expected | PASSED | The function is working properly

## void manageAccountsMenu()
Test Suite 19 - Manage Accounts function
Test case 1 | Test Details
| ID | 19 | Created by | Kristian Lalev
| Function | void manageAccountsMenu() | Created on | 2021-03-04
| Description | This function manages your account | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Deleting your account | 1 | void deleteAccount() | As expected | PASSED | The function is working properly
| 1.2 | Edit account password | 2 | void editPassword() | As expected | PASSED | The function is working properly
| 1.3 | To back out of this menu | 9 | To get back from this page | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 19.1 | Created by | Kristian Lalev
| Function | void manageAccountsMenu() | Created on | 2021-03-05
| Description | This function manages your account | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Deleting your account | 1 | void deleteAccount() | As expected | PASSED | The function is working properly
| 2.2 | Edit account password | 2 | void editPassword() | As expected | PASSED | The function is working properly
| 2.3 | To back out of this menu | 9 | To get back from this page | As expected | PASSED | The function is working properly

## void manageTeamsMenu()
Test Suite 20 - Manage Teams menu - Scrum Trainers only!
Test case 1 | Test Details
| ID | 20 | Created by | Kristian Lalev
| Function | void manageTeamsMenu() | Created on | 2021-03-04
| Description | This function manages your team | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Deleting your account | 1 | To delete your account if you are sure | As expected | PASSED | The function is working properly
| 1.2 | Edit team name | 2 | To edit your team name | As expected | PASSED | The function is working properly
| 1.3 | To back out of this menu | 9 | To get back from this page | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 20.1 | Created by | Kristian Lalev
| Function | void manageTeamsMenu() | Created on | 2021-03-05
| Description | This function manages your team | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Deleting your account | 1 | To delete your account if you are sure | As expected | PASSED | The function is working properly
| 2.2 | Edit team name | 2 | To edit your team name | As expected | PASSED | The function is working properly
| 2.3 | To back out of this menu | 9 | To get back from this page | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 20.2 | Created by | Kristian Lalev
| Function | void manageTeamsMenu() | Created on | 2021-03-06
| Description | This function manages your team | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Deleting your account | 1 | To delete your account if you are sure | As expected | PASSED | The function is working properly
| 3.2 | Edit team name | 2 | To edit your team name | As expected | PASSED | The function is working properly
| 3.3 | To back out of this menu | 9 | To get back from this page | As expected | PASSED | The function is working properly

## void viewEmails()
Test Suite 21 - View emails menu testing
Test case 1 | Test Details
| ID | 21 | Created by | Kristian Lalev
| Function | void viewEmails() | Created on | 2021-03-04
| Description | This function views all the emails in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checks emails | 1 | To check the emails in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 21.1 | Created by | Kristian Lalev
| Function | void viewEmails() | Created on | 2021-03-05
| Description | This function views all the emails in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checks emails | 1 | To check the emails in the system | As expected | PASSED | The function is working properly

## bool checkAccStudentsId()
Test Suite 22 - Checking students accounts id testing
Test case 1 | Test Details
| ID | 22 | Created by | Kristian Lalev
| Function | bool checkAccStudentsId() | Created on | 2021-03-04
| Description | This function checks the ID of the students and the role in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking your password | parola1 | To check your password in the system | As expected | PASSED | The function is working properly
| 1.3 | Specific tokens | 0,1,2,3 | To give the number of token to a special role | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 22.1 | Created by | Kristian Lalev
| Function | bool checkAccStudentsId() | Created on | 2021-03-05
| Description | This function checks the ID of the students and the role in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking your password | parola1 | To check your password in the system | As expected | PASSED | The function is working properly
| 2.3 | Specific tokens | 0,1,2,3 | To give the number of token to a special role | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 22.2 | Created by | Kristian Lalev
| Function | bool checkAccStudentsId() | Created on | 2021-03-05
| Description | This function checks the ID of the students and the role in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 3.2 | Checking your password | parola1 | To check your password in the system | As expected | PASSED | The function is working properly
| 3.3 | Specific tokens | 0,1,2,3 | To give the number of token to a special role | As expected | PASSED | The function is working properly

## bool checkAccTeachersId()
Test Suite 23 - Checking teachers accounts id testing
Test case 1 | Test Details
| ID | 23 | Created by | Kristian Lalev
| Function | bool checkAccTeachersId() | Created on | 2021-03-04
| Description | This function checks the ID of the teachers | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking your password | parola3 | To check your password in the system | As expected | PASSED | The function is working properly
| 1.3 | Specific tokens | 4 | To give the number 4 to a specific role to the teacher | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 23.1 | Created by | Kristian Lalev
| Function | bool checkAccTeachersId() | Created on | 2021-03-05
| Description | This function checks the ID of the teachers | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking your password | parola3 | To check your password in the system | As expected | PASSED | The function is working properly
| 2.3 | Specific tokens | 4 | To give the number 4 to a specific role to the teacher | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 23.2 | Created by | Kristian Lalev
| Function | bool checkAccTeachersId() | Created on | 2021-03-06
| Description | This function checks the ID of the teachers | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the name | danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 3.2 | Checking your password | parola3 | To check your password in the system | As expected | PASSED | The function is working properly
| 3.3 | Specific tokens | 4 | To give the number 4 to a specific role to the teacher | As expected | PASSED | The function is working properly

## bool checkAccAdminId()
Test Suite 24 - Checking admin accounts testing
Test case 1 | Test Details
| ID | 24 | Created by | Kristian Lalev
| Function | bool checkAccAdminId() | Created on | 2021-03-04
| Description | This function checks the ID of the teachers | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | plamen | To check your name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking your password | parola1 | To check your password in the system | As expected | PASSED | The function is working properly
| 1.3 | Specific tokens | 5 | Number 5 is a token to the teacher and the system accepts the account as an admin | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 24.1 | Created by | Kristian Lalev
| Function | bool checkAccAdminId() | Created on | 2021-03-06
| Description | This function checks the ID of the teachers | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | plamen | To check your name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking your password | parola1 | To check your password in the system | As expected | PASSED | The function is working properly
| 2.3 | Specific tokens | 5 | Number 5 is a token to the teacher and the system accepts the account as an admin | As expected | PASSED | The function is working properly

## bool isCharacter()
Test Suite 25 - Checking the characters
Test case 1 | Test Details
| ID | 25 | Created by | Kristian Lalev
| Function | bool isCharacter() | Created on | 2021-03-03
| Description | This function checks the characters in the name | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-04
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | plamen | To check the letters from a to z capital or small letters | As expected | PASSED | The function is working properly

## bool isEmailValid()
Test Suite 26 - Checking the email
Test case 1 | Test Details
| ID | 26 | Created by | Kristian Lalev
| Function | bool isEmailValid() | Created on | 2021-03-04
| Description | This function checks if the email is valid | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the @ | kalalev18@codingburgas.bg | To check the @ in the email | As expected | PASSED | The function is working properly
| 1.2 | Checking the . | kalalev18@codingburgas.bg | To check the . In the email | As expected | PASSED | The function is working properly
Test case 1 | Test Details
| ID | 26.1 | Created by | Kristian Lalev
| Function | bool isEmailValid() | Created on | 2021-03-05
| Description | This function checks if the email is valid | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the @ | kalalev18@codingburgas.bg | To check the @ in the email | As expected | PASSED | The function is working properly
| 2.2 | Checking the . | kalalev18@codingburgas.bg | To check the . In the email | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 26.2 | Created by | Kristian Lalev
| Function | bool isEmailValid() | Created on | 2021-03-05
| Description | This function checks if the email is valid | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the @ | kalalev18@codingburgas.bg | To check the @ in the email | As expected | PASSED | The function is working properly
| 3.2 | Checking the . | kalalev18@codingburgas.bg | To check the . In the email | As expected | PASSED | The function is working properly

## bool isClassnameValid()
Test Suite 27 - Checking the class
Test case 1 | Test Details
| ID | 27 | Created by | Kristian Lalev
| Function | bool isClassnameValid() | Created on | 2021-03-04
| Description | This function checks the class of the student | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the class | 10A, 10B, 10V, 10G | To check the class in the school | As expected | PASSED | The function is working properly
| 1.2 | The error | 10E | Invalid input, try again: | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 27.1 | Created by | Kristian Lalev
| Function | bool isClassnameValid() | Created on | 2021-03-05
| Description | This function checks the class of the student | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the class | 10A, 10B, 10V, 10G | To check the class in the school | As expected | PASSED | The function is working properly
| 2.2 | The error | 10E | Invalid input, try again: | As expected | PASSED | The function is working properly

## int tokenize()
Test Suite 28 - Checking the tokens
Test case 1 | Test Details
| ID | 28 | Created by | Kristian Lalev
| Function | int tokenize() | Created on | 2021-03-05
| Description | This function checks the tokens for the roles in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the tokens | 0 | To be checked as a Scrum Trainer | As expected | PASSED | The function is working properly
| 1.2 | Checking the tokens | 1 | To be checked as a Back-End | As expected | PASSED | The function is working properly
| 1.3 | Checking the tokens | 2 | To be checked as a Front-End | As expected | PASSED | The function is working properly
| 1.4 | Checking the tokens | 3 | To be checked as a QAEngineer | As expected | PASSED | The function is working properly
| 1.5 | Checking the tokens | 4 | To be checked as a teacher | As expected | PASSED | The function is working properly
| 1.6 | Checking the tokens | 5 | To be checked as an admin | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 28.1 | Created by | Kristian Lalev
| Function | int tokenize() | Created on | 2021-03-06
| Description | This function checks the tokens for the roles in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the tokens | 0 | To be checked as a Scrum Trainer | As expected | PASSED | The function is working properly
| 2.2 | Checking the tokens | 1 | To be checked as a Back-End | As expected | PASSED | The function is working properly
| 2.3 | Checking the tokens | 2 | To be checked as a Front-End | As expected | PASSED | The function is working properly
| 2.4 | Checking the tokens | 3 | To be checked as a QAEngineer | As expected | PASSED | The function is working properly
| 2.5 | Checking the tokens | 4 | To be checked as a teacher | As expected | PASSED | The function is working properly
| 2.6 | Checking the tokens | 5 | To be checked as an admin | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 28.2 | Created by | Kristian Lalev
| Function | int tokenize() | Created on | 2021-03-06
| Description | This function checks the tokens for the roles in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the tokens | 0 | To be checked as a Scrum Trainer | As expected | PASSED | The function is working properly
| 3.2 | Checking the tokens | 1 | To be checked as a Back-End | As expected | PASSED | The function is working properly
| 3.3 | Checking the tokens | 2 | To be checked as a Front-End | As expected | PASSED | The function is working properly
| 3.4 | Checking the tokens | 3 | To be checked as a QAEngineer | As expected | PASSED | The function is working properly
| 3.5 | Checking the tokens | 4 | To be checked as a teacher | As expected | PASSED | The function is working properly
| 3.6 | Checking the tokens | 5 | To be checked as an admin | As expected | PASSED | The function is working properly

## void displayStudents()
Test Suite 29 - Display students function testing
Test case 1 | Test Details
| ID | 29 | Created by | Kristian Lalev
| Function | void displayStudents() | Created on | 2021-03-05
| Description | This function displays the students in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking the surname | lalev | To check your surname in the system | As expected | PASSED | The function is working properly
| 1.3 | Checking the password | parola4 | To check the password in the system | As expected | PASSED | The function is working properly
| 1.4 | Checking the class | 10G | To check your class in the system | As expected | PASSED | The function is working properly
| 1.5 | Checking the email | kalalev18@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly
| 1.6 | Checking the role | QAEngineer | To check your role in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 29.1 | Created by | Kristian Lalev
| Function | void displayStudents() | Created on | 2021-03-06
| Description | This function displays the students in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking the surname | lalev | To check your surname in the system | As expected | PASSED | The function is working properly
| 2.3 | Checking the password | parola4 | To check the password in the system | As expected | PASSED | The function is working properly
| 2.4 | Checking the class | 10G | To check your class in the system | As expected | PASSED | The function is working properly
| 2.5 | Checking the email | kalalev18@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly
| 2.6 | Checking the role | QAEngineer | To check your role in the system | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 29.2 | Created by | Kristian Lalev
| Function | void displayStudents() | Created on | 2021-03-07
| Description | This function displays the students in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the name | kristian | To check your name in the system | As expected | PASSED | The function is working properly
| 3.2 | Checking the surname | lalev | To check your surname in the system | As expected | PASSED | The function is working properly
| 3.3 | Checking the password | parola4 | To check the password in the system | As expected | PASSED | The function is working properly
| 3.4 | Checking the class | 10G | To check your class in the system | As expected | PASSED | The function is working properly
| 3.5 | Checking the email | kalalev18@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly
| 3.6 | Checking the role | QAEngineer | To check your role in the system | As expected | PASSED | The function is working properly

## void displayTeachers()
Test Suite 30 - Display teachers function testing
Test case 1 | Test Details
| ID | 30 | Created by | Kristian Lalev
| Function | void displayTeachers() | Created on | 2021-03-05
| Description | This function displays the teachers in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | Danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking the surname | Stamatova | To check your surname in the system | As expected | PASSED | The function is working properly
| 1.3 | Checking the password | parola3 | To check the password in the system | As expected | PASSED | The function is working properly
| 1.4 | Checking the email | dstamatova@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 30.1 | Created by | Kristian Lalev
| Function | void displayTeachers() | Created on | 2021-03-06
| Description | This function displays the teachers in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | Danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking the surname | Stamatova | To check your surname in the system | As expected | PASSED | The function is working properly
| 2.3 | Checking the password | parola3 | To check the password in the system | As expected | PASSED | The function is working properly
| 2.4 | Checking the email | dstamatova@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 30.2 | Created by | Kristian Lalev
| Function | void displayTeachers() | Created on | 2021-03-07
| Description | This function displays the teachers in the school | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the name | Danaila | To check your name in the system | As expected | PASSED | The function is working properly
| 3.2 | Checking the surname | Stamatova | To check your surname in the system | As expected | PASSED | The function is working properly
| 3.3 | Checking the password | parola3 | To check the password in the system | As expected | PASSED | The function is working properly
| 3.4 | Checking the email | dstamatova@codingburgas.bg | To check your email in the system | As expected | PASSED | The function is working properly

## void displayTeams()
Test Suite 31 - Display teams function testing
Test case 1 | Test Details
| ID | 31 | Created by | Kristian Lalev
| Function | void displayTeams() | Created on | 2021-03-05
| Description | This function displays the the info about the teams in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the name | Kristian | To accept the name in the system | As expected | PASSED | The function is working properly
| 1.2 | Checking the description | Stamatova | To accept the surname in the system | As expected | PASSED | The function is working properly
| 1.3 | Checking the date | 2021-03-05 | To accept the date in the system | As expected | PASSED | The function is working properly
| 1.4 | Checking the back-end | Plamen Kostov | To accept the back-end name in the system | As expected | PASSED | The function is working properly
| 1.5 | Checking the front-end | Ilian Yanev | To accept the front-end name in the system | As expected | PASSED | The function is working properly
| 1.6 | Checking the QAEngineer | Kristian Lalev | To accept the QAEngineer name in the system | As expected | PASSED | The function is working properly
| 1.7 | Checking the Scrum Trainer | Plamen Kostov | To accept the Scrum Trainer name in the system | As expected | PASSED | The function is working properly
| 1.8 | Checking the teacher | Danaila Stamatova | To accept the teacher name in the system | As expected | PASSED | The function is working properly
| 1.9 | Checking the status | notuse | To accept the status in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 31.1 | Created by | Kristian Lalev
| Function | void displayTeams() | Created on | 2021-03-06
| Description | This function displays the the info about the teams in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the name | Kristian | To accept the name in the system | As expected | PASSED | The function is working properly
| 2.2 | Checking the description | Stamatova | To accept the surname in the system | As expected | PASSED | The function is working properly
| 2.3 | Checking the date | 2021-03-05 | To accept the date in the system | As expected | PASSED | The function is working properly
| 2.4 | Checking the back-end | Plamen Kostov | To accept the back-end name in the system | As expected | PASSED | The function is working properly
| 2.5 | Checking the front-end | Ilian Yanev | To accept the front-end name in the system | As expected | PASSED | The function is working properly
| 2.6 | Checking the QAEngineer | Kristian Lalev | To accept the QAEngineer name in the system | As expected | PASSED | The function is working properly
| 2.7 | Checking the Scrum Trainer | Plamen Kostov | To accept the Scrum Trainer name in the system | As expected | PASSED | The function is working properly
| 2.8 | Checking the teacher | Danaila Stamatova | To accept the teacher name in the system | As expected | PASSED | The function is working properly
| 2.9 | Checking the status | notuse | To accept the status in the system | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 31.2 | Created by | Kristian Lalev
| Function | void displayTeams() | Created on | 2021-03-07
| Description | This function displays the the info about the teams in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the name | Kristian | To accept the name in the system | As expected | PASSED | The function is working properly
| 3.2 | Checking the description | Stamatova | To accept the surname in the system | As expected | PASSED | The function is working properly
| 3.3 | Checking the date | 2021-03-05 | To accept the date in the system | As expected | PASSED | The function is working properly
| 3.4 | Checking the back-end | Plamen Kostov | To accept the back-end name in the system | As expected | PASSED | The function is working properly
| 3.5 | Checking the front-end | Ilian Yanev | To accept the front-end name in the system | As expected | PASSED | The function is working properly
| 3.6 | Checking the QAEngineer | Kristian Lalev | To accept the QAEngineer name in the system | As expected | PASSED | The function is working properly
| 3.7 | Checking the Scrum Trainer | Plamen Kostov | To accept the Scrum Trainer name in the system | As expected | PASSED | The function is working properly
| 3.8 | Checking the teacher | Danaila Stamatova | To accept the teacher name in the system | As expected | PASSED | The function is working properly
| 3.9 | Checking the status | notuse | To accept the status in the system | As expected | PASSED | The function is working properly

## void displayParticularBackEnd()
Test Suite 32 - Display particular back-end function testing
Test case 1 | Test Details
| ID | 32 | Created by | Kristian Lalev
| Function | void displayParticularBackEnd() | Created on | 2021-03-05
| Description | This function displays the back-ends students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the token for back-end | 2 | To accept the token as if it is a back-end | As expected | PASSED | The function is working properly
| 1.2 | Checking the status for back-end | notuse | To accept the status | As expected | PASSED | The function is working properly
| 1.3 | To show the accounts with token 2 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 32.1 | Created by | Kristian Lalev
| Function | void displayParticularBackEnd() | Created on | 2021-03-06
| Description | This function displays the back-ends students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the token for back-end | 2 | To accept the token as if it is a back-end | As expected | PASSED | The function is working properly
| 2.2 | Checking the status for back-end | notuse | To accept the status | As expected | PASSED | The function is working properly
| 2.3 | To show the accounts with token 2 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly

## void displayPart...FrontEnd()
Test Suite 33 - Display particular front-end function testing
Test case 1 | Test Details
| ID | 33 | Created by | Kristian Lalev
| Function | void displayParticularFrontEnd() | Created on | 2021-03-05
| Description | This function displays particular front-end students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the token for front-end | 1 | To accept the token as if it is a front-end | As expected | PASSED | The function is working properly
| 1.2 | Checking the status for front-end | notuse | To accept the status | As expected | PASSED | The function is working properly
| 1.3 | To show the accounts with token 3 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 33.1 | Created by | Kristian Lalev
| Function | void displayParticularFrontEnd() | Created on | 2021-03-06
| Description | This function displays particular front-end students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the token for front-end | 1 | To accept the token as if it is a front-end | As expected | PASSED | The function is working properly
| 2.2 | Checking the status for front-end | notuse | To accept the status | As expected | PASSED | The function is working properly
| 2.3 | To show the accounts with token 3 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly

## void displayPart...StudentsQA()
Test Suite 34 - Display particular QAEngineer function testing
Test case 1 | Test Details
| ID | 34 | Created by | Kristian Lalev
| Function | void displayParticularStudentsQA() | Created on | 2021-03-05
| Description | This function displays particular QAEngineer students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the token for QAEngineer | 3 | To accept the token as if it is a QAEngineer | As expected | PASSED | The function is working properly
| 1.2 | Checking the status for QAEngineer | notuse | To accept the status | As expected | PASSED | The function is working properly
| 1.3 | To show the accounts with token 3 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 34.1 | Created by | Kristian Lalev
| Function | void displayParticularStudentsQA() | Created on | 2021-03-06
| Description | This function displays particular QAEngineer students | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the token for QAEngineer | 3 | To accept the token as if it is a QAEngineer | As expected | PASSED | The function is working properly
| 2.2 | Checking the status for QAEngineer | notuse | To accept the status | As expected | PASSED | The function is working properly
| 2.3 | To show the accounts with token 3 and "notuse" as info |  | To accept the date in the system | As expected | PASSED | The function is working properly

## void displayTeachersForTeams()
Test Suite 35 - Display particular teacher function testing
Test case 1 | Test Details
| ID | 35 | Created by | Kristian Lalev
| Function | void displayTeachersForTeams() | Created on | 2021-03-05
| Description | This function displays the teacher for its teams | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Name of the teacher | Danaila | To accept the name of the teacher | As expected | PASSED | The function is working properly
| 1.2 | Checking the account and its team |  | To say that in what team the teacher is | As expected | PASSED | The function is working properly
Test Details
Test case 2 | ID | 35.1 | Created by | Kristian Lalev
| Function | void displayTeachersForTeams() | Created on | 2021-03-06
| Description | This function displays the teacher for its teams | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Name of the teacher | Danaila | To accept the name of the teacher | As expected | PASSED | The function is working properly
| 2.2 | Checking the account and its team |  | To say that in what team the teacher is | As expected | PASSED | The function is working properly

## void changeStudentsStatus()
Test Suite 36 - Changing student status function testing
Test case 1 | Test Details
| ID | 36 | Created by | Kristian Lalev
| Function | void changeStudentsStatus() | Created on | 2021-03-06
| Description | This function displays changes the student status | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Checking the status | notuse | To check the status | As expected | PASSED | The function is working properly
| 1.2 | Unexisting status | not | To check if the status doesn’t exist | As expected | PASSED | The function is working properly
| 1.3 | Removing |  | To change the status if you have one | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 36.1 | Created by | Kristian Lalev
| Function | void changeStudentsStatus() | Created on | 2021-03-06
| Description | This function displays changes the student status | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Checking the status | notuse | To check the status | As expected | PASSED | The function is working properly
| 2.2 | Unexisting status | not | To check if the status doesn’t exist | As expected | PASSED | The function is working properly
| 2.3 | Removing |  | To change the status if you have one | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 36.2 | Created by | Kristian Lalev
| Function | void changeStudentsStatus() | Created on | 2021-03-07
| Description | This function displays changes the student status | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Checking the status | notuse | To check the status | As expected | PASSED | The function is working properly
| 3.2 | Unexisting status | not | To check if the status doesn’t exist | As expected | PASSED | The function is working properly
| 3.3 | Removing |  | To change the status if you have one | As expected | PASSED | The function is working properly

## void deleteAccount()
Test Suite 37 - Delete account function testing
Test case 1 | Test Details
| ID | 37 | Created by | Kristian Lalev
| Function | void deleteAccount() | Created on | 2021-03-05
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Name of the user | Kristian | To delete the user with name "Kristian" | As expected | PASSED | The function is working properly
| 1.2 | Go back | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 37.1 | Created by | Kristian Lalev
| Function | void deleteAccount() | Created on | 2026-03-07
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Name of the user | Kristian | To delete the user with name "Kristian" | As expected | PASSED | The function is working properly
| 2.2 | Go back | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 36.2 | Created by | Kristian Lalev
| Function | void deleteAccount() | Created on | 2021-03-07
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Name of the user | Kristian | To delete the user with name "Kristian" | As expected | PASSED | The function is working properly
| 3.2 | Go back | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly

## void editPassword()
Test Suite 38 - Edit password function testing
Test case 1 | Test Details
| ID | 38 | Created by | Kristian Lalev
| Function | void editPassword() | Created on | 2021-03-05
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Name of the user | Kristian | To watch out for "New password: " | As expected | PASSED | The function is working properly
| 1.2 | New password | parola69 | Your passowrd to be changed to parola69 | As expected | PASSED | The function is working properly
| 1.3 | User checking | parola69 | To check if there is user with the old password with name Kristian | As expected | PASSED | The function is working properly
| 1.4 | Editing password |  | "Editing password done!" | As expected | PASSED | The function is working properly
| 1.5 | Go to manageAccounts Menu() | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 38.1 | Created by | Kristian Lalev
| Function | void editPassword() | Created on | 2021-03-06
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-06
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Name of the user | Kristian | To watch out for "New password: " | As expected | PASSED | The function is working properly
| 2.2 | New password | parola69 | Your passowrd to be changed to parola69 | As expected | PASSED | The function is working properly
| 2.3 | User checking | parola69 | To check if there is user with the old password with name Kristian | As expected | PASSED | The function is working properly
| 2.4 | Editing password |  | "Editing password done!" | As expected | PASSED | The function is working properly
| 2.5 | Go to manageAccounts Menu() | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 38.2 | Created by | Kristian Lalev
| Function | void editPassword() | Created on | 2021-03-07
| Description | This function delets any account of the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-07
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Name of the user | Kristian | To watch out for "New password: " | As expected | PASSED | The function is working properly
| 3.2 | New password | parola69 | Your passowrd to be changed to parola69 | As expected | PASSED | The function is working properly
| 3.3 | User checking | parola69 | To check if there is user with the old password with name Kristian | As expected | PASSED | The function is working properly
| 3.4 | Editing password |  | "Editing password done!" | As expected | PASSED | The function is working properly
| 3.5 | Go to manageAccounts Menu() | 1 | To go to manageAccountMenu() | As expected | PASSED | The function is working properly

## void deleteTeams()
Test Suite 39 - Delete teams function testing
Test case 1 | Test Details
| ID | 39 | Created by | Kristian Lalev
| Function | void deleteTeams() | Created on | 2021-03-14
| Description | This function delets any team in the system (Admin only) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-14
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 1.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 1.3 | Checking if the team doesn't exist | BazarBG | "Error!" because this team doesn’t exist | As expected | PASSED | The function is working properly
| 1.4 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 39.1 | Created by | Kristian Lalev
| Function | void deleteTeams() | Created on | 2021-03-14
| Description | This function delets any team in the system (Admin only) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 2.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 2.3 | Checking if the team doesn't exist | BazarBG | "Error!" because this team doesn’t exist | As expected | PASSED | The function is working properly
| 2.4 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 39.2 | Created by | Kristian Lalev
| Function | void deleteTeams() | Created on | 2021-03-15
| Description | This function delets any team in the system (Admin only) | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 3.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 3.3 | Checking if the team doesn't exist | BazarBG | "Error!" because this team doesn’t exist | As expected | PASSED | The function is working properly
| 3.4 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly

## void editTeamName()
Test Suite 40 - Editing the name of the team function testing
Test case 1 | Test Details
| ID | 40 | Created by | Kristian Lalev
| Function | void editTeamName() | Created on | 2021-03-14
| Description | This function edits the name of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-14
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 1.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 1.3 | New team name | MasterBG | To change the name team to be MasterBG | As expected | PASSED | The function is working properly
| 1.4 | Checking the original team name |  | To checks if some team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 1.5 | Changing the name of the existing team |  | The new name team to be MasterBG | As expected | PASSED | The function is working properly
| 1.6 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 40.1 | Created by | Kristian Lalev
| Function | void editTeamName() | Created on | 2021-03-14
| Description | This function edits the name of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 2.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 2.3 | New team name | MasterBG | To change the name team to be MasterBG | As expected | PASSED | The function is working properly
| 2.4 | Checking the original team name |  | To checks if some team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 2.5 | Changing the name of the existing team |  | The new name team to be MasterBG | As expected | PASSED | The function is working properly
| 2.6 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 40.2 | Created by | Kristian Lalev
| Function | void editTeamName() | Created on | 2021-03-15
| Description | This function edits the name of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 3.2 | Checking the team |  | To accept the team because it exists. | As expected | PASSED | The function is working properly
| 3.3 | New team name | MasterBG | To change the name team to be MasterBG | As expected | PASSED | The function is working properly
| 3.4 | Checking the original team name |  | To checks if some team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 3.5 | Changing the name of the existing team |  | The new name team to be MasterBG | As expected | PASSED | The function is working properly
| 3.6 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly

## void editTeamStatus()
Test Suite 41 - Editing the status of the team function testing
Test case 1 | Test Details
| ID | 41 | Created by | Kristian Lalev
| Function | void editTeamStatus() | Created on | 2021-03-14
| Description | This function edits the status of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-14
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 1.2 | Checking the status | 1 | To change the status from active to notactive | As expected | PASSED | The function is working properly
| 1.3 | Checking the team | ZaFe | To checks if the team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 1.4 | Changing the status done |  | The status to be changed to notactive | As expected | PASSED | The function is working properly
| 1.5 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test Details
Test case 2 | ID | 41.1 | Created by | Kristian Lalev
| Function | void editTeamStatus() | Created on | 2021-03-14
| Description | This function edits the status of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 2.2 | Checking the status | 1 | To change the status from active to notactive | As expected | PASSED | The function is working properly
| 2.3 | Checking the team | ZaFe | To checks if the team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 2.4 | Changing the status done |  | The status to be changed to notactive | As expected | PASSED | The function is working properly
| 2.5 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly
Test Details
| ID | 41.2 | Created by | Kristian Lalev
Test case 3 | Function | void editTeamStatus() | Created on | 2021-03-15
| Description | This function edits the status of an existing team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Start-up menu | ZaFe | "Name of the team: " | As expected | PASSED | The function is working properly
| 3.2 | Checking the status | 1 | To change the status from active to notactive | As expected | PASSED | The function is working properly
| 3.3 | Checking the team | ZaFe | To checks if the team with the name ZaFe exists | As expected | PASSED | The function is working properly
| 3.4 | Changing the status done |  | The status to be changed to notactive | As expected | PASSED | The function is working properly
| 3.5 | Go back | 1 | To go back to the manageTeamsMenu() | As expected | PASSED | The function is working properly

## void reports()
Test Suite 42 - reports function testing
Test case 1 | Test Details
| ID | 42 | Created by | Kristian Lalev
| Function | void reports() | Created on | 2021-03-14
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Entering option choice (1) | 1 | To show the list of the students who participate in a particular team | As expected | PASSED | The function is working properly
| 1.2 | Entering option choice (2) | 2 | To show the list of the teachers who do not have an allocated team | As expected | PASSED | The function is working properly
| 1.3 | Entering option choice (3) | 3 | To show the list of the teams which are not full of four students | As expected | PASSED | The function is working properly
| 1.4 | Entering option choice (9) | 9 | To go back to adminMenu() | As expected | PASSED | The function is working properly
| 1.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 42.1 | Created by | Kristian Lalev
| Function | void reports() | Created on | 2021-03-15
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Entering option choice (1) | 1 | To show the list of the students who participate in a particular team | As expected | PASSED | The function is working properly
| 2.2 | Entering option choice (2) | 2 | To show the list of the teachers who do not have an allocated team | As expected | PASSED | The function is working properly
| 2.3 | Entering option choice (3) | 3 | To show the list of the teams which are not full of four students | As expected | PASSED | The function is working properly
| 2.4 | Entering option choice (9) | 9 | To go back to adminMenu() | As expected | PASSED | The function is working properly
| 2.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 42.2 | Created by | Kristian Lalev
| Function | void reports() | Created on | 2021-03-15
| Description | This functions shows the start-up menu when you open that school system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Entering option choice (1) | 1 | To show the list of the students who participate in a particular team | As expected | PASSED | The function is working properly
| 3.2 | Entering option choice (2) | 2 | To show the list of the teachers who do not have an allocated team | As expected | PASSED | The function is working properly
| 3.3 | Entering option choice (3) | 3 | To show the list of the teams which are not full of four students | As expected | PASSED | The function is working properly
| 3.4 | Entering option choice (9) | 9 | To go back to adminMenu() | As expected | PASSED | The function is working properly
| 3.5 | Entering option choice (everything except 1,2,3 and 9) | 5 | "Not an integer, try again: " | As expected | PASSED | The function is working properly

## void checkForMissingMember()
Test Suite 43 - Checking for a missing member function testing (Scrum Master only)
Test case 1 | Test Details
| ID | 43 | Created by | Kristian Lalev
| Function | void checkForMissingMember() | Created on | 2021-03-14
| Description | This function checks for a missing member for a team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-14
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 1 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 1.1 | Start-up menu |  | "Your team: Name: Description: Backend: Frontend: QA engineer: Teacher: Scrum Master:" | As expected | PASSED | The function is working properly
| 1.2 | Checking the 8th token | 8 | If it is 8, then you can input if someone is missing in some position in your team and will display Back-end students with no team | As expected | PASSED | The function is working properly
| 1.3 | Add a back-end if you don't have one in your team | Plamen Kostov | Plamen Kostov doesn't have a team, so he is the chosen one to join ZaFe to be the back-end of the team | As expected | PASSED | The function is working properly
| 1.4 | Add a front-end if you don't have one in your team | Ilian Yanev | Ilian Yanev doesn't have a team, so he is the chosen one to join ZaFe for the front-end part | As expected | PASSED | The function is working properly
| 1.5 | Add a QAEngineer if you don't have one in your team | Kristian Lalev | Kristian Lalev doesn't have a team, so he is the chosen one to join ZaFe for QAEngineering | As expected | PASSED | The function is working properly
| 1.6 | Add a teacher in your team if you don't have one | Danaila Stamatova | Danaila Stamatova is the teacher of that team. | As expected | PASSED | The function is working properly
| 1.7 | Full team |  | If your Scrum Master has already registered 3 more students and 1 more teacher, your team is full and ready for work | As expected | PASSED | The function is working properly
Test case 2 | Test Details
| ID | 43.1 | Created by | Kristian Lalev
| Function | void checkForMissingMember() | Created on | 2021-03-14
| Description | This function checks for a missing member for a team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 2 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 2.1 | Start-up menu |  | "Your team: Name: Description: Backend: Frontend: QA engineer: Teacher: Scrum Master:" | As expected | PASSED | The function is working properly
| 2.2 | Checking the 8th token | 8 | If it is 8, then you can input if someone is missing in some position in your team and will display Back-end students with no team | As expected | PASSED | The function is working properly
| 2.3 | Add a back-end if you don't have one in your team | Plamen Kostov | Plamen Kostov doesn't have a team, so he is the chosen one to join ZaFe to be the back-end of the team | As expected | PASSED | The function is working properly
| 2.4 | Add a front-end if you don't have one in your team | Ilian Yanev | Ilian Yanev doesn't have a team, so he is the chosen one to join ZaFe for the front-end part | As expected | PASSED | The function is working properly
| 2.5 | Add a QAEngineer if you don't have one in your team | Kristian Lalev | Kristian Lalev doesn't have a team, so he is the chosen one to join ZaFe for QAEngineering | As expected | PASSED | The function is working properly
| 2.6 | Add a teacher in your team if you don't have one | Danaila Stamatova | Danaila Stamatova is the teacher of that team. | As expected | PASSED | The function is working properly
| 2.7 | Full team |  | If your Scrum Master has already registered 3 more students and 1 more teacher, your team is full and ready for work | As expected | PASSED | The function is working properly
Test case 3 | Test Details
| ID | 43.2 | Created by | Kristian Lalev
| Function | void checkForMissingMember() | Created on | 2021-03-15
| Description | This function checks for a missing member for a team in the system | Modified by | Kristian Lalev
|  |  | Last modified on | 2021-03-15
Steps
| # | Description | Test Data | Expectations | Actual Result | Status | Comments
| 3 | Starting the function |  |  | As expected | PASSED | The function is working properly
| 3.1 | Start-up menu |  | "Your team: Name: Description: Backend: Frontend: QA engineer: Teacher: Scrum Master:" | As expected | PASSED | The function is working properly
| 3.2 | Checking the 8th token | 8 | If it is 8, then you can input if someone is missing in some position in your team and will display Back-end students with no team | As expected | PASSED | The function is working properly
| 3.3 | Add a back-end if you don't have one in your team | Plamen Kostov | Plamen Kostov doesn't have a team, so he is the chosen one to join ZaFe to be the back-end of the team | As expected | PASSED | The function is working properly
| 3.4 | Add a front-end if you don't have one in your team | Ilian Yanev | Ilian Yanev doesn't have a team, so he is the chosen one to join ZaFe for the front-end part | As expected | PASSED | The function is working properly
| 3.5 | Add a QAEngineer if you don't have one in your team | Kristian Lalev | Kristian Lalev doesn't have a team, so he is the chosen one to join ZaFe for QAEngineering | As expected | PASSED | The function is working properly
| 3.6 | Add a teacher in your team if you don't have one | Danaila Stamatova | Danaila Stamatova is the teacher of that team. | As expected | PASSED | The function is working properly
| 3.7 | Full team |  | If your Scrum Master has already registered 3 more students and 1 more teacher, your team is full and ready for work | As expected | PASSED | The function is working properly